## Product Backlog (Scrum)
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | R | Business Process | Type | Primary Actors | Secondary Actors | Comments | Acceptance Criteria | Completeness Criteria | User Acceptance Test Case ID | Comments
1 | 1 | Standard document | High | PECUNIABANK:001 | Design Documentation for Backend application | Satyam | Satyam | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 20.5 hrs | Design is fullfilled agaist Business requirement
| 2 | Standard document |  | PECUNIABANK:002 | Test Plan | Satyam | Satyam | Average | Low |  | RD:Business Requirement Doc | Non-Functional |  |  |  |  | 8 hrs | Check the test case is fullfiled with user accepance criteria document
2 | 3 | Standard document | High | PECUNIABANK:003 | Bootstrapping the project | Satyam | Satyam | Simple | Low | RD:1 Application SetUp | RD: PecuniaBankDocument_ver1 | Non-Functional |  |  |  |  | 3 hrs | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | 4 | Work session | High | PECUNIABANK:004 | Entity Class and TableDEsign and Populating the data | Satyam | Satyam | Complex | Low | RD2: Entity Class Design and RD3: Table Design | RD: PecuniaBankDocument_ver2 | Functional |  |  |  |  | 7 hrs | Checking against the Table design in RD
4 | 5 | Work session | High | PECUNIABANK:005 | Add Branch,Employee,Customer,Create Account,update ,delete,performe transcation,loan request | Satyam | Satyam | Complex | Low | RD 4: Making Service And Dao for Module | RD:PecuniaBankDocument_ver3 | Functional |  |  |  |  | 13 hrs | Test Implemented Service Using Postman
5 | 6 | Work session | High | PECUNIABANK:006 | Performe Transaction,Loan Ledger,Passbook | Satyam | Satyam | Complex | Low | RD7: Performe Operation | RD: PecuniaBankDocument_ver4 | Functional |  |  |  |  | 13 hrs | Performe Customer operation using bank Employee on Postman
6 | 7 | Work session
7 | 8
8 | 9
9 | 10
10 | 11
11 | 12
12 | 13
13 | 14
14 | 15
Sprint 2 | Sprint 2
15 | 16 | Standard document | High | PECUNIABANK:007 | Design Documentation fo Angular application | Satyam | Satyam | Complex | Low | RD): Business Requirement DOc | RD: Business Requirement and User accepatance Criteria | Non Functional |  |  |  |  | 5hr | Design the Wireframe in copy and Start working With angular
| 17 | Standard document | High | PECUNIABANK:008 | Test Plan | Satyam | Satyam |  | Low | Making Components |  | Non Functional |  |  |  |  | 3hr | Test validate according to components Design
16 | 18 | Standard document |  | PECUNIABANK:009 | Design a home page having standard menus | Satyam |  | Complex | Medium | Along with test |  | Functional |  |  |  |  | 5hr | Desing the nav bar where attach the components and make flow is correct
17 | 19 |  |  | PECUNIABANK:010 | Implement of Components and service | Satyam | Satyam | Complex | Medium | Implement the Service in components |  | Functional |  |  |  |  | 9hr | Implements services with components and connected to STS
18 | 20
19 | 21
20 | 22 |  |  | PECUNIABANK:011 | Testing individual parts | Satyam | Satyam | Complex | Medium | Test the Application using Angular and Spring boot |  | Functional |  |  |  |  | 7hr | Test the Project is working Fine Both angullar and spring boot.
21 | 23
22 | 24
23 | 25
24 | 26
25 | 27
26 | 28
27 | 29
28 | 30
29 | 31
30 | 32
33
31 | 34
32 | 35
33 | 36
34 | 37
35 | 38
36 | 39
37 | 40
38 | 41
39 | 42
40 | 43
41 | 44
42 | 45
43 | 46
44 | 47
45 | 48
46 | 49
Note on A3: This column is used to Link back to the Full MoSCoW list for the project (RD.045 sheet).
Note on B3: This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog
Note on C3: This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.).
Note on D3: Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have
Note on E3: Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW.
Note on F3: Brief description of the requirements necessary to fulfill the objective
Note on G3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on H3: Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party.
Note on I3: Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex
Note on J3: Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low).
Note on K3: Used if reference is needed to another work product that provides further detail of the requirement. Examples include RA.027 Candidate Business Rules, RA.090 Reporting Fit Analysis, RA.027 Use Case Details, RD.070 Audit and Control Requirements), DS.030 Application Set-up Documents.
Note on L3: Column to document the originating process where the process is defined and necessary. For example, a process that originates from either Current Process Model [RD.030] or Future Process Model [RD.011].
Note on M3: Defines whether the User Story is Functional, Non-Functional or Technical type.
Note on N3: Column provides linkage to primary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on O3: Column provides linkage to secondary actors defined in RA.023 (Use Case Model) and/or RD.005 (System Context Diagram)
Note on P3: Use column for supporting comments.
Note on Q3: Column for defining the agreed upon acceptance criteria
Note on R3: Description of the condition(s) that indicate the requirement has been satisfied.
Note on S3: This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied.
Note on T3: This column is used to provide supporting information, such as changes to the original requirement.
When using a Scrum approach to project management, use this sheet to document the Product Backlog, as captured in User Stories.

## Sprint Backlog 2
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
| PECUNIABANK:007 | 1 | Wireframes and story boarding for each task | All Team | 2020-04-27 | 5hr | 0hr | completed | 5
|  | 2 | Routing Url List | All Team
|  | 3 | Data classes details
|  | 4 | Angular service
|  | 5 | Components details
|  | 6 | Detail about the security
| PECUNIABANK:008 | 1 | service in Angular | All Team | 2020-04-28 | 3hr | 0hr | completed | 3
|  | 2 | Check data flow and mapping
| PECUNIABANK:009 | 1 | Designing menu in template |  | 2020-04-29 | 5hr | 0hr | completed | 5
|  | 2 | Adding Routing details
|  | 3 | Displaying standard info or advertisement
| PECUNIABANK:010 | 1 | connection between backend and frontend |  | 2020-04-30 | 6hr | 0hr | completed | 6
|  | 2 | Component sends the details to service
|  | 3 | Make url toconnect to backend with front end
|  | 4 | Check the data transfer between frontend and backend
|  |  | Check the operation of service is working fine with both end |  | 2020-04-01 | 3hr | 0hr | completed | 3
Handling error in Frontend
| PECUNIABANK:011 |  | Checking project is working or not handling the error and or not and verify important comment |  | 2020-04-01 | 4hr | 0hr | completed | 4
|  |  | Check all the written test cases and implement the backend test case |  | 2020-05-02 | 3hr | 0hr | completed | 3
| PECUNIABANK:012 |  | Testing and Modification continue
[5 empty] | 2020-05-04 | to | 2020-05-07 | completed
List User Story steps that were not completed at Sprint End
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## Sprint Backlog 1
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | PECUNIABANK:001 | 1 | Entity Class Design | All team members | 2020-04-16 | 3 hrs | 0 hrs | Completed | 3
|  | 2 | Table Design | All team members | 2020-04-16 | 2 hrs | 0 hrs | Completed | 2
|  | 3 | Application Architecture | All team members | 2020-04-17 | 1 hrs | 0 hrs | Completed | 1
|  | 4 | Use case diagram | All team members | 2020-04-17 | 2 hrs | 0.5 hrs | Completed | 1.5
|  | 5 | Sequence Diagram | All team members | 2020-04-17 | 2 hrs | 1 hr | Completed | 2
|  | 6 | Each use case detail description | All team members | 2020-04-20 | 3 hrs | 0 hrs | Completed | 3
|  | 7 | Class Layer diagram | All team members | 2020-04-20 | 2 hrs | 0.5 hrs | Completed | 2
|  | 8 | Class Diagram | All team members | 2020-04-21 | 2 hrs |  | Completed
|  | 9 | Webservice URL Details | All team members | 2020-04-21 | 2 hrs |  | Completed
Completed
2 | PECUNIABANK:002 | 1 | Test plan for dao, | All team members | 2020-04-21 |  |  | Completed
|  | 2 | Test plan for service | All team members | 2020-04-21 |  |  | Completed
|  | 3 | Test plan for webservice methods | All team members | 2020-04-22 |  |  | Completed
3 | PECUNIABANK:003 | 1 | Creating a Spring boot starter project | All team members | 2020-04-17 | 1 hrs | 0 hrs | Completed | 1 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it | All team members | 2020-04-17 | 1 hrs | 0 hrs | Completed | 0.5 hrs
|  | 3 | Adding server, jpa properties in application.properties | All team members | 2020-04-17 | 1 hrs | 0 hrs | Completed | 0.5 hrs
4 | PECUNIABANK:004 | 1 | Entity Class Design | All team members | 2020-04-21 | 2hr |  | Completed
|  | 2 | Check tables are poulated in DB | All team members |  | 2hr
|  | 3 | Populate the Data | All team members |  | 3hr
5 | PECUNIABANK:005 | 1 | Using Entity Manager performe Dao operation | All team members | 2020-04-22 | 10hr |  | Completed | 7hr
|  | 2 | Write few JPQL query to performe Custom operation in Dao | All team members
|  | 3 | Write code for testing purpose to check all entity class are created and work fine or not | All team members
|  | 4 | Check the RestController Part using print Simple add object in database for checking purpose | All team members | 2020-04-23 | 3hr |  |  | 3hr
6 | PECUNIABANK:006 | 1 | Make Service Interface Related to Module for implementing method | All team members | 2020-04-23 | 5hr |  | Completed
|  | 2 | Make Dao classes or Every Functionality related to Module | All team members
|  | 3 | Check all Function by Command Line Runner | All team members
|  | 4 | Make Restcontroller for each Module | All team members | 2020-04-24 | 8hr
|  | 5 | Making url and Function inside the restcontroller class | All team members
|  | 6 | Check the Function using Postman | All team members
|  | 7 | Apply Exception in Service as well as in restcontroller.
List User Story steps that were not completed at Sprint End
Note on A3: This column is used to trace each row of this spreadsheet back to a specific row on the MoSCoW List worksheet.
Note on B3: This column is used to document the Use Case Identifier.
Note on D3: Task Step description. You would only use this column when detailing User Stories using the short form as described in RA.021. If you are using the long form of the User Stories template you may eliminate this column.
Note on E3: List the Scrum team members assigned to this task.
Note on F3: Column is used to document the date the task was assigned
Note on G3: Use this column to provide Initial Scrum team estimate of effort for the task step to be completed, may be numbers of days or hours.
Note on H3: Adjusted estimate after the Sprint has begun
Note on I3: Task status: Started In Progress Completed Cancelled Deferred to Sprint <Sprint number>
Note on J3: Actual Effort - after the step has been completed a number indicating how many hours or days. This number will be used to prepare the burndown chart.
Note on K3: Use this column to provide supporting information such as changes to the original requirement.
Note on M3: This column is used to link the requirements to any resulting modules (software).
Note on N3: This column is used to link the requirements/use cases to the test scenarios.
Note on O3: This column is used to link the requirements/use cases to the test scenarios.
Note on P3: This column is used to link the requirements/use cases to the test scenarios.
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.